## Sheet1
Site | Status | Phase | UAT signoff (including form functionality) Y/N | Go live date | Customer consent (Y/N) | Customer signoff in pre-prod (Y/N) | Colour code
bigbeard.co.za | UAT testing | POC | Y | 26/11/2025 | Y | Y | Red not planned
Amandakartz.co.za | pre-prod | Pilot | Y | 2025-03-12 | Big Beard managed | Big Beard managed | Orange planned
Competencesa.co.za | pre-prod | Pilot | Y | 2025-03-12 | Big Beard managed | Big Beard managed
Swimforrivers.co.za | pre-prod | Pilot | Y | 2025-03-12 | Big Beard managed | Big Beard managed
trpfs.co.za | pre-prod | Pilot | Y | 2025-03-12 | Big Beard managed | Big Beard managed
bullocksbeans.co.za | pre-prod | Pilot | Y | 2025-03-12 | Big Beard managed | Big Beard managed
natroecuticspartnerbrands.com | pre-prod | Phase 1 | Y | 2025-10-12 | Big Beard managed | Big Beard managed
FurnellandAssociates.co.za | pre-prod | Phase 1 |  | 2025-10-12
Aftsarepository.co.za | pre-prod | Pilot | Y | 2025-10-12 | Big Beard managed | Big Beard managed
Deborahatkins.co.za | pre-prod | Phase 1 |  | 2025-10-12 |  |  | Green switched over
victor.co.za | pre-prod | Phase 1 |  | 2025-10-12
BenjaminCommodities.co.za | pre-prod | Phase 1 |  | 2025-10-12
suscan.co.za | pre-prod | Phase 1 |  | 2025-10-12
anelehomecare.co.za | pre-prod | Phase 1 |  | 2025-10-12
boironrange.co.za | pre-prod | Phase 1 |  | 2025-10-12
caseforward.co.za | pre-prod | Phase 1 |  | 2025-10-12
denkercapital.co.za | pre-prod | Phase 1 |  | 2025-10-12
gecn.com | pre-prod | Phase 1 |  | 2025-10-12
huisnuweland.co.za | pre-prod | Phase 1 |  | 2025-10-12
justtransition.co.za | pre-prod | Phase 2 |  | 14/12/2025
mavenflooring.co.za | pre-prod | Phase 2 |  | 14/12/2025
methodixsolutions.co.za | pre-prod | Phase 2 |  | 14/12/2025
panoramaps.co.za | pre-prod | Phase 2 |  | 14/12/2025
rusileather.co.za | pre-prod | Phase 2 |  | 14/12/2025
sosimpleenergy.co.za | pre-prod | Phase 2 |  | 14/12/2025
southerncrossbeach.co.za | pre-prod | Phase 2 |  | 14/12/2025
stafpro.co.za | pre-prod | Phase 2 |  | 14/12/2025
thetippingpoint.co.za | pre-prod | Phase 2 |  | 14/12/2025
thetransitiontank.co.za | pre-prod | Phase 2 |  | 14/12/2025
euroconcepts.co.za | pre-prod | Phase 2 |  | 14/12/2025
Northbaptist.co.za | pre-prod | Phase 2 |  | 14/12/2025
http://metisonline.co.za/ | pre-prod | Phase 2 |  | 14/12/2025
sunscan.co.za | pre-prod | Phase 2 |  | 14/12/2025
rusileather.com | pre-prod | Phase 2 |  | 14/12/2025
thetippingpoint.co.za | pre-prod | Phase 2 |  | 14/12/2025
21century.co.za | pre-prod | Phase 2 |  | 14/12/2025
aupairhive.com | pre-prod | Phase 2 |  | 14/12/2025
jeanique.co.za | pre-prod | Phase 2 |  | 14/12/2025
lamica.co.za | xneelo | Phase 3 |  | 2026-01-01
markberger.co.za | xneelo | Phase 3 |  | 2026-01-01
barno.co.za | xneelo | Phase 3 |  | 2026-01-01
payments.fairygodmother.co.za | xneelo | Phase 3 |  | 2026-01-01
moneymagicprogram.com | xneelo | Phase 3 |  | 2026-01-01
hasa-members.co.za | xneelo | Phase 3 |  | 2026-01-01
oratilekids.co.za | xneelo | Phase 3 |  | 2026-01-01
southerncrossbeach.co.za | xneelo | Phase 3 |  | 2026-01-01
vikingbeds.co.za | xneelo | Phase 3 |  | 2026-01-01
inharmony-health.com | xneelo | Phase 3 |  | 2026-01-01
blankbottle.co.za | xneelo | Phase 3 |  | 2026-01-01
fairygodmotherinc.com | xneelo | Phase 3 |  | 2026-01-01
festivemagic.fairygodmotherinc.com | xneelo | Phase 3 |  | 2026-01-01
bullocksbeans.co.za | xneelo | Phase 3 |  | 2026-01-01
fallencovidheroes.co.za | xneelo | Phase 3 |  | 2026-01-01
beautybuy.co.za | xneelo | Phase 3 |  | 2026-01-01
shop.fairygodmotherinc.com | xneelo | Phase 3 |  | 2026-01-01
skinsoothe.co.za | xneelo | Phase 3 |  | 2026-01-01
metis.agency | defects/placeholders
atkinsfurnell.co.za | defects/placeholders
secretpjsociety.com | defects/placeholders
benjamincommodities.com | defects/placeholders
fairygodmother.co.za | defects/placeholders
stributique.co.za | defects/placeholders
docx.metisunicorns.co.za | defects/placeholders
stributique.com | defects/placeholders
gpcid.co.za | defects/placeholders
okcid.co.za | defects/placeholders
medexpert.co.za | defects/placeholders
natroecuticspartnerbrands.co.za | defects/placeholders
gpokcid.co.za | defects/placeholders
michie-made.co.za | defects/placeholders